Voss & Delaney launch - weekly-20260811_140015-Meeting Transcript

11 August 2026, 02:00pm

16m 09s

Gemma Ashworth started transcription

Gemma Ashworth   0:04

Okay, it's just the four of us today, Colin sat in on last Monday's one but he's off this week, so, Raj, Louise, Tobias, let's crack on.

Raj Patel   0:12

Yep.

Louise Corrigan   0:13

Ready.

Tobias Frank   0:14

Mm-hmm.

Gemma Ashworth   0:18

So the big one is the Voss and Delaney launch. Marguerite emailed me on Friday, she's getting twitchy about the date.

Louise Corrigan   0:25

She always is. What did she want?

Gemma Ashworth   0:28

She wants to know if we can still hit the fifteenth. And honestly I don't think we can, the print's the bottleneck.

Tobias Frank   0:35

Yeah, Kettleby Print quoted us a ten day lead time on the brochures, so if we send artwork this week we're looking at, what, the twentieth at the earliest.

Raj Patel   0:44

That's if I get the proofs to them by Wednesday. Which I can, they're nearly there.

Gemma Ashworth   0:49

Okay, so let's, let's make that firm. Raj, can you get the artwork proofs over to Kettleby by Wednesday?

Raj Patel   0:55

Yeah, I'll send the artwork proofs to Kettleby Print by Wednesday. No problem.

Gemma Ashworth   1:00

Great. And I'll reply to Marguerite today and tell her the realistic date is the twentieth, not the fifteenth, and manage her expectations.

Louise Corrigan   1:07

Good, better she hears it now than the week of.

Gemma Ashworth   1:10

Exactly. So we're deciding, we move the launch to the twentieth. Everyone okay with that?

Tobias Frank   1:15

Yeah.

Raj Patel   1:16

Agreed.

Louise Corrigan   1:16

Fine by me.

Gemma Ashworth   1:20

Right. Oh, and David asked me yesterday whether we'd finished the case study for the website, so that's clearly on his radar now.

Louise Corrigan   1:27

Of course it is, he mentioned it to me too in the corridor.

Tobias Frank   1:30

Sorry, my mic. Yeah, the case study, that's basically done, I sent the draft round last week.

Louise Corrigan   1:36

You did, I've read it, it's good. I already sent the signed contract back to Voss and Delaney as well, so that side's all closed off.

Gemma Ashworth   1:43

Oh brilliant, that's one less thing.

Louise Corrigan   1:46

Yeah, that's done and dusted.

Raj Patel   1:49

Mm.

Gemma Ashworth   1:53

One risk on the print, and Tobias flag if I'm wrong, but Kettleby have let us down on timings before, haven't they.

Tobias Frank   1:59

They have. If they slip even two days we miss the twentieth as well, so it's tight. I'd build in a bit of buffer mentally.

Gemma Ashworth   2:06

Noted. Let's just watch it closely. Anything else? Hannah from finance is joining next week's, so we can do the budget bit then, not today.

Raj Patel   2:14

Works for me, I don't have the numbers yet anyway.

Louise Corrigan   2:17

Yeah, next week for that.

Tobias Frank   2:19

Mm-hmm.

Gemma Ashworth   2:23

Right, that's us then. Raj, proofs to the printers by Wednesday, I'll square Marguerite off today, and we reconvene with Hannah next week. Thanks folks.

Raj Patel   2:31

Cheers.

Louise Corrigan   2:32

Bye all.

Tobias Frank   2:33

See you.

Gemma Ashworth stopped transcription